## Backlog
Epic Key | Epic Title | Story Key | Story Title | Description | Story Points | MVL | Priority | Status | Sprint
EP-1 | Authentication & user management | HM-1 | User registration with role selection | Business buyer (B2B), individual (B2C), grower — metadata passed to trigger | 3 | Yes | High | To Do
EP-1 | Authentication & user management | HM-2 | Email/password login with redirect | Redirects to role-based dashboard after login | 2 | Yes | High | To Do
EP-1 | Authentication & user management | HM-3 | Supabase Auth trigger — auto-create profile row | handle_new_user trigger with CASE-based role assignment | 3 | Yes | High | To Do
EP-1 | Authentication & user management | HM-4 | Dashboard role router | Middleware-free role detection on /dashboard page | 2 | Yes | High | To Do
EP-1 | Authentication & user management | HM-5 | Sign out — client-side with full cache clear | window.location.href redirect to bypass middleware | 1 | Yes | High | To Do
EP-1 | Authentication & user management | HM-6 | Password reset flow | Supabase magic link / OTP reset | 2 | No | Medium | To Do
EP-1 | Authentication & user management | HM-7 | Admin ABN verification for B2B buyers | Admin approves/revokes B2B status from buyers page | 3 | Yes | High | To Do
EP-1 | Authentication & user management | HM-8 | Backfill existing auth users missing profiles | SQL migration for users with null role | 1 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-9 | Public marketplace page with category filters | All listed products, B2B/B2C toggle, category sidebar | 3 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-10 | Product card with correct price display | B2B shows ex-GST + inc-GST hint; B2C shows retail inc-GST | 2 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-11 | Add to cart with quantity input | Editable number input between − and + buttons, capped at available stock | 3 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-12 | Cart persists in session storage | Zustand + sessionStorage, cleared on checkout complete | 2 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-13 | Market open/closed banner | isMarketOpen() check — Wed 8am–8pm AEST | 1 | Yes | High | To Do
EP-2 | Marketplace & product discovery | HM-14 | Listing window open/closed for farmers | isListingWindowOpen() — Sun midnight to Tue 23:59 AEST | 1 | Yes | Medium | To Do
EP-2 | Marketplace & product discovery | HM-15 | Product search by name or farm | Client-side filter on marketplace page | 2 | No | Low | To Do
EP-2 | Marketplace & product discovery | HM-16 | Product detail page | Full product description, farm info, reviews | 3 | No | Low | To Do
EP-3 | Orders & fulfilment | HM-17 | Checkout page — fulfillment selection | Hub pickup (free) or delivery ($20), hub selector from delivery_zones | 3 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-18 | Order summary with GST breakdown | B2B: ex-GST lines + GST row + total inc-GST; B2C: retail inc-GST | 3 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-19 | Create order API — atomic stock deduction | checkout_reserve_stock RPC, order_items insert, rollback on failure | 5 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-20 | Test mode — bypass Stripe for order creation | NEXT_PUBLIC_TEST_MODE=true auto-confirms order | 1 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-21 | Buyer orders page — collapsible table | Expandable rows, line items, totals, Orders + Invoices tabs | 5 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-22 | Per-order CSV export | CSV with ex-GST, GST, total columns per order | 2 | Yes | Medium | To Do
EP-3 | Orders & fulfilment | HM-23 | Print-ready tax invoice | Opens in new tab, auto-triggers print dialog, ABN shown | 3 | Yes | Medium | To Do
EP-3 | Orders & fulfilment | HM-24 | Buyer order detail page | /dashboard/buyer/orders/[id] with status and items | 2 | Yes | High | To Do
EP-3 | Orders & fulfilment | HM-25 | Dispute window — buyer can raise dispute | 6hr window post-delivery, dispute API route | 3 | No | Medium | To Do
EP-3 | Orders & fulfilment | HM-26 | PPOD — proof of placement photo upload | Cloudinary upload per order item, auto-triggers delivered | 3 | Yes | High | To Do
EP-4 | Payments & payouts | HM-27 | Stripe checkout — payment intent creation | Stripe Connect charge, idempotent, rollback on failure | 5 | Yes | High | To Do
EP-4 | Payments & payouts | HM-28 | Stripe webhook handler | payment_intent.succeeded → confirm order status | 3 | Yes | High | To Do
EP-4 | Payments & payouts | HM-29 | Farmer Stripe Connect onboarding | /api/stripe/onboarding creates Express account, redirects to hosted form | 5 | Yes | High | To Do
EP-4 | Payments & payouts | HM-30 | Stripe onboarding verify & complete pages | Verify charges_enabled + payouts_enabled after return | 2 | Yes | High | To Do
EP-4 | Payments & payouts | HM-31 | Inngest payout job — post dispute window | Auto-triggers 6hrs after delivered, calculates commission, transfers to farmer | 5 | Yes | High | To Do
EP-4 | Payments & payouts | HM-32 | Commission rate per farmer | commission_rate on farmers table, defaults to config commission_rate_default | 2 | Yes | High | To Do
EP-4 | Payments & payouts | HM-33 | Payout record written to payouts table | gross, commission_cents, net_amount_cents stored, idempotent | 2 | Yes | High | To Do
EP-4 | Payments & payouts | HM-34 | Farmer payouts dashboard | Earnings page with payout history and Stripe onboarding banner | 3 | Yes | High | To Do
EP-4 | Payments & payouts | HM-35 | Admin payouts overview | All farmers, gross + commission split, payout status | 2 | No | Medium | To Do
EP-4 | Payments & payouts | HM-36 | Refund flow — admin triggered | Stripe refund + order status → refunded | 3 | No | Medium | To Do
EP-5 | Farmer / grower dashboard | HM-37 | Farmer storefront — create/edit farm profile | Business name, bio, location, brand colour | 3 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-38 | Inventory list with B2B/B2C stock split | Shows wholesale ex-GST and B2C retail inc-GST per product | 3 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-39 | New product page | Form with category, unit, wholesale price, stock, GST toggle, listing toggle | 3 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-40 | Edit product page | Pre-filled form, delete button, stock split preview from config | 3 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-41 | Farmer orders page | Orders containing their products, status advance buttons | 3 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-42 | Status: payment_confirmed → preparing | Farmer clicks Start Preparing | 1 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-43 | Status: preparing → ready_for_pickup | Farmer clicks Mark Ready | 1 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-44 | Status: ready → dispatch | Farmer clicks Dispatch | 1 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-45 | Status: dispatch → delivered (hub pickup) | Farmer clicks Mark Delivered for hub orders | 1 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-46 | PPOD auto-delivers (direct delivery) | All items have photo → status auto-set to delivered | 2 | Yes | High | To Do
EP-5 | Farmer / grower dashboard | HM-47 | Listing toggle locked outside window | is_listed_this_week toggle disabled when listing window closed | 1 | Yes | Medium | To Do
EP-5 | Farmer / grower dashboard | HM-48 | B2C stock split preview on product form | Reads b2b_stock_pct from config, not hardcoded 0.8 | 2 | Yes | Medium | To Do
EP-6 | Admin dashboard | HM-49 | Admin overview page | Order counts, revenue, pending approvals | 3 | Yes | High | To Do
EP-6 | Admin dashboard | HM-50 | Admin orders — observer view | All orders with status labels; no advance buttons (farmer owns chain) | 2 | Yes | High | To Do
EP-6 | Admin dashboard | HM-51 | Admin growers page | Approve/reject farmers, ABN verified toggle | 3 | Yes | High | To Do
EP-6 | Admin dashboard | HM-52 | Admin buyers page | B2B/B2C buyers, verify ABN, upgrade/downgrade role | 3 | Yes | High | To Do
EP-6 | Admin dashboard | HM-53 | Admin config editor | Live edit platform config: commission, markup, stock split, listing window | 3 | Yes | High | To Do
EP-6 | Admin dashboard | HM-54 | Admin payouts page | All payout records, gross + net + commission per farmer | 2 | No | Medium | To Do
EP-6 | Admin dashboard | HM-55 | Admin dispute management | View disputes, mark resolved, trigger refund | 3 | No | Medium | To Do
EP-6 | Admin dashboard | HM-56 | Packing list view | Grouped by farmer for market-day pick/pack | 2 | No | Low | To Do
EP-6 | Admin dashboard | HM-57 | Picking list view | Grouped by buyer for dispatch | 2 | No | Low | To Do
EP-7 | Infrastructure & platform | HM-58 | Supabase RLS — all tables secured | profiles, orders, order_items, products, farmers, payouts | 5 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-59 | Fix RLS infinite recursion | SECURITY DEFINER function farmer_has_order() breaks circular dependency | 3 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-60 | createAdminClient using plain supabase-js | Not @supabase/ssr — avoids cookie session interfering with service role | 2 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-61 | Next.js middleware — auth-only, skip API routes | No DB queries in middleware; API routes handle own auth | 2 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-62 | Inngest background jobs setup | Heartbeat, market open, payout trigger, dispute expiry | 3 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-63 | Cloudinary integration for product images | Upload widget, signed URLs, PPOD storage | 2 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-64 | All migrations in order (001–010) | Schema, RLS, trigger fixes, hub seed, Stripe verified_at | 3 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-65 | Remove test mode before production | Remove NEXT_PUBLIC_TEST_MODE=true from .env.local | 1 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-66 | Environment variables documented | .env.example with all required keys | 1 | No | Medium | To Do
EP-7 | Infrastructure & platform | HM-67 | Vercel deployment with production env vars | All secrets in Vercel dashboard, not in code | 2 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-68 | GST-compliant pricing logic | B2B wholesale ex-GST, B2C retail with 45% markup + 10% GST | 2 | Yes | High | To Do
EP-7 | Infrastructure & platform | HM-69 | AEST timezone utilities | formatAEST, isMarketOpen, isListingWindowOpen helpers | 1 | Yes | High | To Do

## Epics
Epic Key | Epic Title | Total Stories | MVL Stories | Post-MVL Stories | Total Points | MVL Points | Post-MVL Points
EP-1 | Authentication & user management | 8 | 7 | 1 | 17 | 15 | 2
EP-2 | Marketplace & product discovery | 8 | 6 | 2 | 17 | 12 | 5
EP-3 | Orders & fulfilment | 10 | 9 | 1 | 30 | 27 | 3
EP-4 | Payments & payouts | 10 | 8 | 2 | 32 | 27 | 5
EP-5 | Farmer / grower dashboard | 12 | 12 | 0 | 24 | 24 | 0
EP-6 | Admin dashboard | 9 | 5 | 4 | 23 | 14 | 9
EP-7 | Infrastructure & platform | 12 | 11 | 1 | 27 | 26 | 1
| TOTAL | 69 | 58 | 11 | 170 | 145 | 25

## MVL Stories
Epic Key | Epic Title | Story Key | Story Title | Description | Story Points | MVL | Priority | Status | Sprint
EP-1 | Authentication & user management | HM-1 | User registration with role selection | Business buyer (B2B), individual (B2C), grower — metadata passed to trigger | 3 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-2 | Email/password login with redirect | Redirects to role-based dashboard after login | 2 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-3 | Supabase Auth trigger — auto-create profile row | handle_new_user trigger with CASE-based role assignment | 3 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-4 | Dashboard role router | Middleware-free role detection on /dashboard page | 2 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-5 | Sign out — client-side with full cache clear | window.location.href redirect to bypass middleware | 1 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-7 | Admin ABN verification for B2B buyers | Admin approves/revokes B2B status from buyers page | 3 | Yes | High | To Do | Sprint 1
EP-1 | Authentication & user management | HM-8 | Backfill existing auth users missing profiles | SQL migration for users with null role | 1 | Yes | High | To Do | Sprint 1
EP-2 | Marketplace & product discovery | HM-9 | Public marketplace page with category filters | All listed products, B2B/B2C toggle, category sidebar | 3 | Yes | High | To Do | Sprint 1
EP-2 | Marketplace & product discovery | HM-10 | Product card with correct price display | B2B shows ex-GST + inc-GST hint; B2C shows retail inc-GST | 2 | Yes | High | To Do | Sprint 1
EP-2 | Marketplace & product discovery | HM-11 | Add to cart with quantity input | Editable number input between − and + buttons, capped at available stock | 3 | Yes | High | To Do | Sprint 2
EP-2 | Marketplace & product discovery | HM-12 | Cart persists in session storage | Zustand + sessionStorage, cleared on checkout complete | 2 | Yes | High | To Do | Sprint 2
EP-2 | Marketplace & product discovery | HM-13 | Market open/closed banner | isMarketOpen() check — Wed 8am–8pm AEST | 1 | Yes | High | To Do | Sprint 2
EP-2 | Marketplace & product discovery | HM-14 | Listing window open/closed for farmers | isListingWindowOpen() — Sun midnight to Tue 23:59 AEST | 1 | Yes | Medium | To Do | Sprint 2
EP-3 | Orders & fulfilment | HM-17 | Checkout page — fulfillment selection | Hub pickup (free) or delivery ($20), hub selector from delivery_zones | 3 | Yes | High | To Do | Sprint 2
EP-3 | Orders & fulfilment | HM-18 | Order summary with GST breakdown | B2B: ex-GST lines + GST row + total inc-GST; B2C: retail inc-GST | 3 | Yes | High | To Do | Sprint 2
EP-3 | Orders & fulfilment | HM-19 | Create order API — atomic stock deduction | checkout_reserve_stock RPC, order_items insert, rollback on failure | 5 | Yes | High | To Do | Sprint 2
EP-3 | Orders & fulfilment | HM-20 | Test mode — bypass Stripe for order creation | NEXT_PUBLIC_TEST_MODE=true auto-confirms order | 1 | Yes | High | To Do | Sprint 2
EP-3 | Orders & fulfilment | HM-21 | Buyer orders page — collapsible table | Expandable rows, line items, totals, Orders + Invoices tabs | 5 | Yes | High | To Do | Sprint 3
EP-3 | Orders & fulfilment | HM-22 | Per-order CSV export | CSV with ex-GST, GST, total columns per order | 2 | Yes | Medium | To Do | Sprint 3
EP-3 | Orders & fulfilment | HM-23 | Print-ready tax invoice | Opens in new tab, auto-triggers print dialog, ABN shown | 3 | Yes | Medium | To Do | Sprint 3
EP-3 | Orders & fulfilment | HM-24 | Buyer order detail page | /dashboard/buyer/orders/[id] with status and items | 2 | Yes | High | To Do | Sprint 3
EP-3 | Orders & fulfilment | HM-26 | PPOD — proof of placement photo upload | Cloudinary upload per order item, auto-triggers delivered | 3 | Yes | High | To Do | Sprint 3
EP-4 | Payments & payouts | HM-27 | Stripe checkout — payment intent creation | Stripe Connect charge, idempotent, rollback on failure | 5 | Yes | High | To Do | Sprint 3
EP-4 | Payments & payouts | HM-28 | Stripe webhook handler | payment_intent.succeeded → confirm order status | 3 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-29 | Farmer Stripe Connect onboarding | /api/stripe/onboarding creates Express account, redirects to hosted form | 5 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-30 | Stripe onboarding verify & complete pages | Verify charges_enabled + payouts_enabled after return | 2 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-31 | Inngest payout job — post dispute window | Auto-triggers 6hrs after delivered, calculates commission, transfers to farmer | 5 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-32 | Commission rate per farmer | commission_rate on farmers table, defaults to config commission_rate_default | 2 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-33 | Payout record written to payouts table | gross, commission_cents, net_amount_cents stored, idempotent | 2 | Yes | High | To Do | Sprint 4
EP-4 | Payments & payouts | HM-34 | Farmer payouts dashboard | Earnings page with payout history and Stripe onboarding banner | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-37 | Farmer storefront — create/edit farm profile | Business name, bio, location, brand colour | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-38 | Inventory list with B2B/B2C stock split | Shows wholesale ex-GST and B2C retail inc-GST per product | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-39 | New product page | Form with category, unit, wholesale price, stock, GST toggle, listing toggle | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-40 | Edit product page | Pre-filled form, delete button, stock split preview from config | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-41 | Farmer orders page | Orders containing their products, status advance buttons | 3 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-42 | Status: payment_confirmed → preparing | Farmer clicks Start Preparing | 1 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-43 | Status: preparing → ready_for_pickup | Farmer clicks Mark Ready | 1 | Yes | High | To Do | Sprint 5
EP-5 | Farmer / grower dashboard | HM-44 | Status: ready → dispatch | Farmer clicks Dispatch | 1 | Yes | High | To Do | Sprint 6
EP-5 | Farmer / grower dashboard | HM-45 | Status: dispatch → delivered (hub pickup) | Farmer clicks Mark Delivered for hub orders | 1 | Yes | High | To Do | Sprint 6
EP-5 | Farmer / grower dashboard | HM-46 | PPOD auto-delivers (direct delivery) | All items have photo → status auto-set to delivered | 2 | Yes | High | To Do | Sprint 6
EP-5 | Farmer / grower dashboard | HM-47 | Listing toggle locked outside window | is_listed_this_week toggle disabled when listing window closed | 1 | Yes | Medium | To Do | Sprint 6
EP-5 | Farmer / grower dashboard | HM-48 | B2C stock split preview on product form | Reads b2b_stock_pct from config, not hardcoded 0.8 | 2 | Yes | Medium | To Do | Sprint 6
EP-6 | Admin dashboard | HM-49 | Admin overview page | Order counts, revenue, pending approvals | 3 | Yes | High | To Do | Sprint 6
EP-6 | Admin dashboard | HM-50 | Admin orders — observer view | All orders with status labels; no advance buttons (farmer owns chain) | 2 | Yes | High | To Do | Sprint 6
EP-6 | Admin dashboard | HM-51 | Admin growers page | Approve/reject farmers, ABN verified toggle | 3 | Yes | High | To Do | Sprint 6
EP-6 | Admin dashboard | HM-52 | Admin buyers page | B2B/B2C buyers, verify ABN, upgrade/downgrade role | 3 | Yes | High | To Do | Sprint 6
EP-6 | Admin dashboard | HM-53 | Admin config editor | Live edit platform config: commission, markup, stock split, listing window | 3 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-58 | Supabase RLS — all tables secured | profiles, orders, order_items, products, farmers, payouts | 5 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-59 | Fix RLS infinite recursion | SECURITY DEFINER function farmer_has_order() breaks circular dependency | 3 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-60 | createAdminClient using plain supabase-js | Not @supabase/ssr — avoids cookie session interfering with service role | 2 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-61 | Next.js middleware — auth-only, skip API routes | No DB queries in middleware; API routes handle own auth | 2 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-62 | Inngest background jobs setup | Heartbeat, market open, payout trigger, dispute expiry | 3 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-63 | Cloudinary integration for product images | Upload widget, signed URLs, PPOD storage | 2 | Yes | High | To Do | Sprint 7
EP-7 | Infrastructure & platform | HM-64 | All migrations in order (001–010) | Schema, RLS, trigger fixes, hub seed, Stripe verified_at | 3 | Yes | High | To Do | Sprint 8
EP-7 | Infrastructure & platform | HM-65 | Remove test mode before production | Remove NEXT_PUBLIC_TEST_MODE=true from .env.local | 1 | Yes | High | To Do | Sprint 8
EP-7 | Infrastructure & platform | HM-67 | Vercel deployment with production env vars | All secrets in Vercel dashboard, not in code | 2 | Yes | High | To Do | Sprint 8
EP-7 | Infrastructure & platform | HM-68 | GST-compliant pricing logic | B2B wholesale ex-GST, B2C retail with 45% markup + 10% GST | 2 | Yes | High | To Do | Sprint 8
EP-7 | Infrastructure & platform | HM-69 | AEST timezone utilities | formatAEST, isMarketOpen, isListingWindowOpen helpers | 1 | Yes | High | To Do | Sprint 8

## Sprint Plan
Sprint | Story Key | Story Title | Points | Epic | Priority
Sprint 1 | HM-1 | User registration with role selection | 3 | Authentication & user management | High
Sprint 1 | HM-2 | Email/password login with redirect | 2 | Authentication & user management | High
Sprint 1 | HM-3 | Supabase Auth trigger — auto-create profile row | 3 | Authentication & user management | High
Sprint 1 | HM-4 | Dashboard role router | 2 | Authentication & user management | High
Sprint 1 | HM-5 | Sign out — client-side with full cache clear | 1 | Authentication & user management | High
Sprint 1 | HM-7 | Admin ABN verification for B2B buyers | 3 | Authentication & user management | High
Sprint 1 | HM-8 | Backfill existing auth users missing profiles | 1 | Authentication & user management | High
Sprint 1 | HM-9 | Public marketplace page with category filters | 3 | Marketplace & product discovery | High
Sprint 1 | HM-10 | Product card with correct price display | 2 | Marketplace & product discovery | High
Sprint 2 | HM-11 | Add to cart with quantity input | 3 | Marketplace & product discovery | High
Sprint 2 | HM-12 | Cart persists in session storage | 2 | Marketplace & product discovery | High
Sprint 2 | HM-13 | Market open/closed banner | 1 | Marketplace & product discovery | High
Sprint 2 | HM-14 | Listing window open/closed for farmers | 1 | Marketplace & product discovery | Medium
Sprint 2 | HM-17 | Checkout page — fulfillment selection | 3 | Orders & fulfilment | High
Sprint 2 | HM-18 | Order summary with GST breakdown | 3 | Orders & fulfilment | High
Sprint 2 | HM-19 | Create order API — atomic stock deduction | 5 | Orders & fulfilment | High
Sprint 2 | HM-20 | Test mode — bypass Stripe for order creation | 1 | Orders & fulfilment | High
Sprint 3 | HM-21 | Buyer orders page — collapsible table | 5 | Orders & fulfilment | High
Sprint 3 | HM-22 | Per-order CSV export | 2 | Orders & fulfilment | Medium
Sprint 3 | HM-23 | Print-ready tax invoice | 3 | Orders & fulfilment | Medium
Sprint 3 | HM-24 | Buyer order detail page | 2 | Orders & fulfilment | High
Sprint 3 | HM-26 | PPOD — proof of placement photo upload | 3 | Orders & fulfilment | High
Sprint 3 | HM-27 | Stripe checkout — payment intent creation | 5 | Payments & payouts | High
Sprint 4 | HM-28 | Stripe webhook handler | 3 | Payments & payouts | High
Sprint 4 | HM-29 | Farmer Stripe Connect onboarding | 5 | Payments & payouts | High
Sprint 4 | HM-30 | Stripe onboarding verify & complete pages | 2 | Payments & payouts | High
Sprint 4 | HM-31 | Inngest payout job — post dispute window | 5 | Payments & payouts | High
Sprint 4 | HM-32 | Commission rate per farmer | 2 | Payments & payouts | High
Sprint 4 | HM-33 | Payout record written to payouts table | 2 | Payments & payouts | High
Sprint 5 | HM-34 | Farmer payouts dashboard | 3 | Payments & payouts | High
Sprint 5 | HM-37 | Farmer storefront — create/edit farm profile | 3 | Farmer / grower dashboard | High
Sprint 5 | HM-38 | Inventory list with B2B/B2C stock split | 3 | Farmer / grower dashboard | High
Sprint 5 | HM-39 | New product page | 3 | Farmer / grower dashboard | High
Sprint 5 | HM-40 | Edit product page | 3 | Farmer / grower dashboard | High
Sprint 5 | HM-41 | Farmer orders page | 3 | Farmer / grower dashboard | High
Sprint 5 | HM-42 | Status: payment_confirmed → preparing | 1 | Farmer / grower dashboard | High
Sprint 5 | HM-43 | Status: preparing → ready_for_pickup | 1 | Farmer / grower dashboard | High
Sprint 6 | HM-44 | Status: ready → dispatch | 1 | Farmer / grower dashboard | High
Sprint 6 | HM-45 | Status: dispatch → delivered (hub pickup) | 1 | Farmer / grower dashboard | High
Sprint 6 | HM-46 | PPOD auto-delivers (direct delivery) | 2 | Farmer / grower dashboard | High
Sprint 6 | HM-47 | Listing toggle locked outside window | 1 | Farmer / grower dashboard | Medium
Sprint 6 | HM-48 | B2C stock split preview on product form | 2 | Farmer / grower dashboard | Medium
Sprint 6 | HM-49 | Admin overview page | 3 | Admin dashboard | High
Sprint 6 | HM-50 | Admin orders — observer view | 2 | Admin dashboard | High
Sprint 6 | HM-51 | Admin growers page | 3 | Admin dashboard | High
Sprint 6 | HM-52 | Admin buyers page | 3 | Admin dashboard | High
Sprint 7 | HM-53 | Admin config editor | 3 | Admin dashboard | High
Sprint 7 | HM-58 | Supabase RLS — all tables secured | 5 | Infrastructure & platform | High
Sprint 7 | HM-59 | Fix RLS infinite recursion | 3 | Infrastructure & platform | High
Sprint 7 | HM-60 | createAdminClient using plain supabase-js | 2 | Infrastructure & platform | High
Sprint 7 | HM-61 | Next.js middleware — auth-only, skip API routes | 2 | Infrastructure & platform | High
Sprint 7 | HM-62 | Inngest background jobs setup | 3 | Infrastructure & platform | High
Sprint 7 | HM-63 | Cloudinary integration for product images | 2 | Infrastructure & platform | High
Sprint 8 | HM-64 | All migrations in order (001–010) | 3 | Infrastructure & platform | High
Sprint 8 | HM-65 | Remove test mode before production | 1 | Infrastructure & platform | High
Sprint 8 | HM-67 | Vercel deployment with production env vars | 2 | Infrastructure & platform | High
Sprint 8 | HM-68 | GST-compliant pricing logic | 2 | Infrastructure & platform | High
Sprint 8 | HM-69 | AEST timezone utilities | 1 | Infrastructure & platform | High